Note for Record

Phase 1 - Test Project – Project Meeting

Date: 21/01/2026

Time: 10:00

Location: Microsoft Teams

Generated By: developer@scopesight.local

Client: Test Client

Project: Phase 1 - Test Project

Objectives / Agenda

• Finalize the instant management Training Pack
• Review the status of the fraud alert response scenario
• Discuss action items from the weekly call
• Plan mapping of Tom's process

Attendees

| Internal | External |
| --- | --- |
| DM |  |
| HT |  |
| NC |  |
| AW |  |
| MDO |  |

Key Discussion Points

Instant Management Training Pack
• Training Pack is finalized and marked as done.

Fraud Alert Response Scenario
• Ongoing review of the fraud alert response scenario.

Action Items from Weekly Call
• Mapping of letter-driven volume set within queues is pending forecast data.
• Meeting scheduled with audit manager Sarah for further discussion.
• Options to reduce data refresh frequency need exploration.

Mapping Tom's Process
• Awaiting access to Fraud Watch report and MO document for process mapping.

New Actions

| Title | Detail | Owner | Due Date |
| --- | --- | --- | --- |
| Finalize instant management Training Pack | Confirm that the Training Pack is complete and ready for distribution. | HT | TBC |
| Link with audit manager | Dovile to meet with Sarah to discuss audit-related matters. | DM | TBC |
| Explore options for data refresh frequency | Investigate possibilities to reduce the data refresh frequency for cyber source. | HT | TBC |